## COBRA MP
Prism PEO - Master Plan COBRA Renewal & Annual Enrollment
|  | Renewal Date |  |  |  | 0% | (Status: C-Completed, P-In Progress, W-Waiting for Approval, Decision or Information, N-Not Started)
Task Category | Detail | Responsible Org. | Assigned Individuals | Due Date | Completion Date | Percent Complete | Status | Comments
|  | *Specify TP or PEO Responsiblity | *Specify TP or PEO Individuals
Requirements Gathering
| Initiate the OE process and send PEO communication and request for information | ThrivePass | Relationship Manager | 3 months in advance |  | 0% |  | Renewal addendum
| Review service agreement | ThrivePass | Relationship Manager | 3 months in advance |  | 0%
| Renewal addendum received including information on plan changes, preference on active/passive and when PEOs OE will be set up, timing and communication | PEO |  | 2 months in advance |  | 0%
| SBC's received | PEO |  | 1 month in advance |  | 0%
| Run QB Plan Members report to determine COBRA client/division list | ThrivePass | Account Manager/Relationship Manager | 1&2 months in advance |  | 0% |  | Filter by division to track employer groups that need OE set up. PEO should prioritize renewal conversations with these PEOs to ensure OE is set up at least 30 days in advance. Re-run reporting 1 month in advance to catch any changes.
| Prepare OE Tracker | ThrivePass | Relationship Manager | 2 months in advance |  | 0% |  | Save to external drive
| Email COBRA team with OE overview | ThrivePass | Relationship Manager | 2 months in advance |  | 0% |  | RM to email COBRA@thrivepass.com with Ashley Miller and Ryan Chacinski on Cc
| Update OE Tracker when clients/divisions are ready for OE | ThrivePass | Account Manager/RM | 1-2 months in advance |  | 0% |  | AM to do if applicable
| Request client terms | ThrivePass/PEO | Relationship Manager | 1 month in advance |  | 0% |  | Determine if OE should be set up for any terminated clients/divisions
| Review Requirements | ThrivePass | Relationship Manager | 3 months in advance |  | 0%
| Share carrier contact report and remind PEO to update all carriers under Payee ID with the COBRA eligibility contact email | ThrivePass/PEO | Relationship Manager | 2 months in advance |  | 0%
System Set-up
| New plans built in COBRA system if not imported via Plan Add/Update Parser | ThrivePass | COBRA Product Support Specialist |  |  | 0% |  | Incuding terminated clients
| New rates added to COBRA system via the Plan Add/Update Parser weekly | ThrivePass | Files team |  |  | 0%
| PEO validation of plans and rates | PEO |  |  |  | 0% |  | RM to send Plan Export filtered to show plans and new rate periods. PEO can also view in portal
| PEO validation of active plans | PEO |  |  |  | 0% |  | RM to send PEO RF Report showing the plans that would be offered for each cleint/division OE
| RM to ensure PEO communicates all client renewals | ThrivePass | Relationship Manager | 1 month in advance |  | 0%
| Update divisions that are terming | ThrivePass | COBRA Product Support Specialist |  |  | 0% |  | If applicable
Communications & Letter Customizations
| Provide Standard OE letters for PEO to Review | ThrivePass | Relationship Manager |  |  | 0% |  | OE Notification - shows OE time period, info on plan changes & instructions to enroll via the member portal. Plan Change Notice - Sent once a plan, coverage tier or rate has changed and inlcudes premium schedule. Enrollment Confirmation - Sent upon enrollment and initial premium payment is rcvd for a newly enrolled plan(s) and includes premium schedule.
| OE Notification - edits due | PEO |  | 2 months in advance |  | 0% |  | Customize OE notification on the divisional level
| Update production with finalized Letters | ThrivePass | Relationship Manager | 2 months in advance |  | 0% |  | Option to add static OE period instead of using the variables in the letter utility
Annual Enrollment
| Ensure OE Settings - Plan Year start date is populated | ThrivePass | COBRA Product Support Specialist |  |  | 0%
| Refer to Risk Factor report for setting up new plan year plans/risk factors | ThrivePass | COBRA Product Support Specialist |  |  | 0% |  | Report runs weekly
| Enable all divisions for the OE Utility | ThrivePass | COBRA Product Support Specialist |  |  | 0% |  | OE Notification queued
| Ensure all divisions have been set up for OE | ThrivePass | AM/RM/COBRA Product Support Specialist |  |  | 0% |  | Re-run QB Plan Members report to see if any new divisions need to be set up
| Ensure plan has stop date if going away | ThrivePass | COBRA Product Support Specialist |  |  | 0% |  | Stop date must be applied prior to first day of new PY
| Make sure ACH was not turned off for QB's moving plans | ThrivePass | COBRA Product Support Specialist |  |  | 0% |  | For plan migration
Education
| PEO Playbook | ThrivePass | Relationship Manager |  |  | 0%
| Review COBRA Processed Report | ThrivePass | Relationship Manager |  |  | 0%
Post OE Activity
| Post OE Audit #1 | ThrivePass | COBRA Product Support Specialist | around the PY effective date |  | 0% |  | Audit after OE has been set up to review new enrollments. Run report (ACA Report, QB Plan Summary or use v-lookup on Plan Members report) to look for any enrollments to offer OE
| Post OE Audit #2 | ThrivePass | COBRA Product Support Specialist | 1 month post PY |  | 0% |  | Audit 1 month after OE to review new enrollments. Run report (ACA Report, QB Plan Summary or use v-lookup on Plan Members report) to look for any enrollments to offer OE
| Audit for risk factor updates/active plans that might have been missed | ThrivePass | COBRA Product Support Specialist |  |  | 0% |  | Use Risk Factor Report
| Provide QB Plan Members report to PEO to show enrollments and terminations | ThrivePass | Relationship Manager |  |  | 0%
| Provide PEO with metrics reporting | ThrivePass | Account Manager/RM |  |  | 0%
Processes and Documentation
| ThrivePass to document applicable processes for post renewal handoff | ThrivePass | COBRA Product Support Specialist |  |  | 0%
| Update COBRA Manual with vendor and PEO information | ThrivePass | COBRA Product Support Specialist |  |  | 0%

## Pre-Tax
Prism PEO - Pre-tax Renewal
|  | Renewal Date |  |  |  | #REF! | (Status: C-Completed, P-In Progress, W-Waiting for Approval, Decision or Information, N-Not Started)
Task Category | Detail | Responsible Org. | Assigned Individuals | Due Date | Completion Date | Percent Complete | Status | Comments
|  | *Specify TP or PEO Responsiblity | *Specify TP or PEO Individuals
Requirements Gathering
| Initiate the OE process and send PEO communication and request for information | ThrivePass | Relationship Manager | 3 months in advance |  | 0% |  | Renewal addendum and pre-tax mapping
| Review service agreement | ThrivePass | Relationship Manager | 3 months in advance |  | 0%
| Renewal addendum received | PEO |  | 2 months in advance |  | 0%
| Pre-tax Mapping received | PEO |  | 1 month in advance |  | 0%
| Send renewal addendum and mapping to files@thrivepass.com & TPA@thrivepass.com | ThrivePass | Relationship Manager | 1 month in advance |  | 0%
System Set-up
| Pre-tax team to renew plans and/or build new plans as applicable | ThrivePass | Pre-tax Product Support Specialist | 1 month in advance |  | 0%
| PEO validation of enrollments | PEO |  | Prior to PY start |  | 0% |  | PEO can view in portal
Pre-tax Engagement
| Review Open Enrollment Campaign to help increase adoption and education | ThrivePass | Relationship Manager | 3 months in advance |  | 0%
Education
| PEO Playbook | ThrivePass | Relationship Manager |  |  | 0%
| OE Resources | ThrivePass | Relationship Manager |  |  | 0%
Post OE Activity
| Provide PEO with metrics reporting | ThrivePass | Account Manager/RM | 1 month post OE |  | 0%